## September 1
CONCRETING OF TANAWIN ROAD - LAGUNITA ROAD
BRGY. TUNGKONG MANGGA, SAN JOSE DEL MONTE CITY, BULACAN
WORK ACCOMPLISHMENT: SEPTEMBER 1, 2016
Item No. | Work Description |  | Unit | Qty | Unit Cost | Amount | Weight (%) | Accomplishment (Quantity) |  |  | Amount |  |  | Weight accomplished (%)
[8 empty] | Previous | This period | To Date | Previous | This Period | To Date
100 | Clearing and Grubbing |  | sq.m. | 1758.8 | 16.01 | 28158.39 | 0.29481 |  |  | 0 | 0 | 0 | 0 | 0
103 | Structure Excavation |  | cu.m. | 272.8 | 225.41 | 61491.85 | 0.6438 |  |  | 0 | 0 | 0 | 0 | 0
105 | Subgrade Preparation |  | sq.m. | 6155.8 | 15.11 | 93014.14 | 0.97382 |  | 945 | 945 | 0 | 14278.9503 | 14278.9503 | 0.1495
200 | Aggregate Sub Base Coarse |  | cu.m. | 871 | 618.0757 | 538343.93 | 5.6363 |  | 77.8987 | 77.8987 | 0 | 48147.3165 | 48147.3165 | 0.50409
201 | Aggregate Base Coarse |  | cu.m. | 581 | 731.2165 | 424836.81 | 4.4479 |  | 51.9623 | 51.9623 | 0 | 37995.6961 | 37995.6961 | 0.3978
311 | PCCP(250mmthk @ 14days conc.) |  | sq.m. | 5276.4 | 1124.5 | 5933311.8 | 62.1196 |  | 471.9 | 471.9 | 0 | 530651.55 | 530651.55 | 5.5557
404 | Reinforcing Steel Bar |  | kgs. | 5080.2 | 46.48 | 236127.7 | 2.4722 |  | 0 | 0 | 0 | 0 | 0 | 0
405 | Structural Concrete Class "A" |  | cu.m. | 65.82 | 6001.8899 | 395044.39 | 4.136 |  | 0 | 0 | 0 | 0 | 0 | 0
505 | Grouted Riprap |  | cu.m. | 682 | 2606.63 | 1777721.66 | 18.6121 |  | 0 | 0 | 0 | 0 | 0 | 0
SPL-1 | Project Signboard (DPWH) |  | ea. | 1 | 4026.75 | 4026.75 | 0.042159 |  | 1 | 1 | 0 | 4026.75 | 4026.75 | 0.042159
SPL-2 | Project Signboard (COA) |  | ea. | 1 | 7805.7 | 7805.7 | 0.081723 |  | 0 | 0 | 0 | 0 | 0 | 0
SPL-3 | Const. Safety and Health |  | l.s. | 1 | 51542.4 | 51542.4 | 0.53963 |  | 1 | 1 | 0 | 51542.4 | 51542.4 | 0.53963
TOTAL AMOUNT | [5 empty] | 9551425.52 | 100 |  |  |  | 0 | 686642.6628 | 686642.6628 | 7.1889
|  | Prepared By : |  |  |  |  | Checked By:
|  |  | __________________________ |  |  |  |  | _______________________________
|  |  | CHARLON O. QUIMINALES |  |  |  |  | MYRNA O. POLICARPIO
|  |  | Project Engineer |  |  |  |  | General Manager
F-PIM-004
Rev. 0 09/19/14
WEEKLY ACCOMPLISHMENT
REPORT

## Sep 15
CONCRETING OF TANAWIN ROAD - LAGUNITA ROAD
BRGY. TUNGKONG MANGGA, SAN JOSE DEL MONTE CITY, BULACAN
WORK ACCOMPLISHMENT: SEPTEMBER 15, 2016
Item No. | Work Description |  | Unit | Qty | Unit Cost | Amount | Weight (%) | Accomplishment (Quantity) |  |  | Amount |  |  | Weight accomplished (%)
[8 empty] | Previous | This period | To Date | Previous | This Period | To Date
100 | Clearing and Grubbing |  | sq.m. | 1758.8 | 16.01 | 28158.39 | 0.29481 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | Structure Excavation |  | cu.m. | 272.8 | 225.41 | 61491.85 | 0.6438 | 0 | 12.8 | 12.8 | 0 | 2885.2481 | 2885.2481 | 0.030208
105 | Subgrade Preparation |  | sq.m. | 6155.8 | 15.11 | 93014.14 | 0.97382 | 945 | 1188.285 | 2133.285 | 14278.9503 | 17954.9867 | 32233.937 | 0.33748
200 | Aggregate Sub Base Coarse |  | cu.m. | 871 | 618.0757 | 538343.93 | 5.6363 | 77.8987 | 223.9453 | 301.844 | 48147.3165 | 138415.1175 | 186562.4339 | 1.9532
201 | Aggregate Base Coarse |  | cu.m. | 581 | 731.2165 | 424836.81 | 4.4479 | 51.9623 | 149.3825 | 201.3448 | 37995.6961 | 109230.9835 | 147226.6796 | 1.5414
311 | PCCP(250mmthk @ 14days conc.) |  | sq.m. | 5276.4 | 1124.5 | 5933311.8 | 62.1196 | 471.9 | 1356.63 | 1828.53 | 530651.55 | 1525530.435 | 2056181.985 | 21.5275
404 | Reinforcing Steel Bar |  | kgs. | 5080.2 | 46.48 | 236127.7 | 2.4722 | 0 | 0 | 0 | 0 | 0 | 0 | 0
405 | Structural Concrete Class "A" |  | cu.m. | 65.82 | 6001.8899 | 395044.39 | 4.136 | 0 | 0 | 0 | 0 | 0 | 0 | 0
505 | Grouted Riprap |  | cu.m. | 682 | 2606.63 | 1777721.66 | 18.6121 | 0 | 6.4 | 6.4 | 0 | 16682.432 | 16682.432 | 0.17466
SPL-1 | Project Signboard (DPWH) |  | ea. | 1 | 4026.75 | 4026.75 | 0.042159 | 1 | 0 | 1 | 4026.75 | 0 | 4026.75 | 0.042159
SPL-2 | Project Signboard (COA) |  | ea. | 1 | 7805.7 | 7805.7 | 0.081723 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPL-3 | Const. Safety and Health |  | l.s. | 1 | 51542.4 | 51542.4 | 0.53963 | 1 | 0 | 1 | 51542.4 | 0 | 51542.4 | 0.53963
TOTAL AMOUNT | [5 empty] | 9551425.52 | 100 |  |  |  | 686642.6628 | 1810699.2028 | 2497341.8656 | 26.1463
|  | Prepared By : |  |  |  |  | Checked By:
|  |  | __________________________ |  |  |  |  | _______________________________
|  |  | CHARLON O. QUIMINALES |  |  |  |  | MYRNA O. POLICARPIO
|  |  | Project Engineer |  |  |  |  | General Manager
F-PIM-004
Rev. 0 09/19/14
WEEKLY ACCOMPLISHMENT
REPORT

## Sep 22
CONCRETING OF TANAWIN ROAD - LAGUNITA ROAD
BRGY. TUNGKONG MANGGA, SAN JOSE DEL MONTE CITY, BULACAN
WORK ACCOMPLISHMENT: SEPTEMBER 22, 2016
Item No. | Work Description |  | Unit | Qty | Unit Cost | Amount | Weight (%) | Accomplishment (Quantity) |  |  | Amount |  |  | Weight accomplished (%)
[8 empty] | Previous | This period | To Date | Previous | This Period | To Date
100 | Clearing and Grubbing |  | sq.m. | 1758.8 | 16.01 | 28158.39 | 0.29481 | 0 | 764.7 | 764.7 | 0 | 12242.8479 | 12242.8479 | 0.12818
103 | Structure Excavation |  | cu.m. | 272.8 | 225.41 | 61491.85 | 0.6438 | 12.8 | 4.4 | 17.2 | 2885.2481 | 991.804 | 3877.0521 | 0.040591
105 | Subgrade Preparation |  | sq.m. | 6155.8 | 15.11 | 93014.14 | 0.97382 | 2133.285 | 543.165 | 2676.45 | 32233.937 | 8207.2233 | 40441.1604 | 0.4234
200 | Aggregate Sub Base Coarse |  | cu.m. | 871 | 618.0757 | 538343.93 | 5.6363 | 301.844 | 76.8538 | 378.6978 | 186562.4339 | 47501.4752 | 234063.9091 | 2.4506
201 | Aggregate Base Coarse |  | cu.m. | 581 | 731.2165 | 424836.81 | 4.4479 | 201.3448 | 51.2653 | 252.6101 | 147226.6796 | 37486.0271 | 184712.7067 | 1.9339
311 | PCCP(250mmthk @ 14days conc.) |  | sq.m. | 5276.4 | 1124.5 | 5933311.8 | 62.1196 | 1828.53 | 465.57 | 2294.1 | 2056181.985 | 523533.465 | 2579715.45 | 27.0087
404 | Reinforcing Steel Bar |  | kgs. | 5080.2 | 46.48 | 236127.7 | 2.4722 | 0 | 0 | 0 | 0 | 0 | 0 | 0
405 | Structural Concrete Class "A" |  | cu.m. | 65.82 | 6001.8899 | 395044.39 | 4.136 | 0 | 0 | 0 | 0 | 0 | 0 | 0
505 | Grouted Riprap |  | cu.m. | 682 | 2606.63 | 1777721.66 | 18.6121 | 6.4 | 53.8 | 60.2 | 16682.432 | 140236.694 | 156919.126 | 1.6429
SPL-1 | Project Signboard (DPWH) |  | ea. | 1 | 4026.75 | 4026.75 | 0.042159 | 1 | 0 | 1 | 4026.75 | 0 | 4026.75 | 0.042159
SPL-2 | Project Signboard (COA) |  | ea. | 1 | 7805.7 | 7805.7 | 0.081723 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPL-3 | Const. Safety and Health |  | l.s. | 1 | 51542.4 | 51542.4 | 0.53963 | 1 | 0 | 1 | 51542.4 | 0 | 51542.4 | 0.53963
TOTAL AMOUNT | [5 empty] | 9551425.52 | 100 |  |  |  | 2497341.8656 | 770199.5365 | 3267541.4022 | 34.21
|  | Prepared By : |  |  |  |  | Checked By:
|  |  | __________________________ |  |  |  |  | _______________________________
|  |  | CHARLON O. QUIMINALES |  |  |  |  | MYRNA O. POLICARPIO
|  |  | Project Engineer |  |  |  |  | General Manager
F-PIM-004
Rev. 0 09/19/14
WEEKLY ACCOMPLISHMENT
REPORT

## Sep 29
CONCRETING OF TANAWIN ROAD - LAGUNITA ROAD
BRGY. TUNGKONG MANGGA, SAN JOSE DEL MONTE CITY, BULACAN
WORK ACCOMPLISHMENT: SEPTEMBER 29, 2016
Item No. | Work Description |  | Unit | Qty | Unit Cost | Amount | Weight (%) | Accomplishment (Quantity) |  |  | Amount |  |  | Weight accomplished (%)
[8 empty] | Previous | This period | To Date | Previous | This Period | To Date
100 | Clearing and Grubbing |  | sq.m. | 1758.8 | 16.01 | 28158.39 | 0.29481 | 764.7 | 82.9 | 847.6 | 12242.8479 | 1327.2291 | 13570.077 | 0.14207
103 | Structure Excavation |  | cu.m. | 272.8 | 225.41 | 61491.85 | 0.6438 | 17.2 | 35.2 | 52.4 | 3877.0521 | 7934.4323 | 11811.4844 | 0.12366
105 | Subgrade Preparation |  | sq.m. | 6155.8 | 15.11 | 93014.14 | 0.97382 | 2676.45 | 290.15 | 2966.6 | 40441.1604 | 4384.1666 | 44825.327 | 0.46931
200 | Aggregate Sub Base Coarse |  | cu.m. | 871 | 618.0757 | 538343.93 | 5.6363 | 378.6978 | 41.0541 | 419.7519 | 234063.9091 | 25374.5234 | 259438.4325 | 2.7162
201 | Aggregate Base Coarse |  | cu.m. | 581 | 731.2165 | 424836.81 | 4.4479 | 252.6101 | 27.3851 | 279.9952 | 184712.7067 | 20024.4323 | 204737.139 | 2.1435
311 | PCCP(250mmthk @ 14days conc.) |  | sq.m. | 5276.4 | 1124.5 | 5933311.8 | 62.1196 | 2294.1 | 248.7 | 2542.8 | 2579715.45 | 279663.15 | 2859378.6 | 29.9367
404 | Reinforcing Steel Bar |  | kgs. | 5080.2 | 46.48 | 236127.7 | 2.4722 | 0 | 0 | 0 | 0 | 0 | 0 | 0
405 | Structural Concrete Class "A" |  | cu.m. | 65.82 | 6001.8899 | 395044.39 | 4.136 | 0 | 0 | 0 | 0 | 0 | 0 | 0
505 | Grouted Riprap |  | cu.m. | 682 | 2606.63 | 1777721.66 | 18.6121 | 60.2 | 57.2 | 117.4 | 156919.126 | 149099.236 | 306018.362 | 3.2039
SPL-1 | Project Signboard (DPWH) |  | ea. | 1 | 4026.75 | 4026.75 | 0.042159 | 1 | 0 | 1 | 4026.75 | 0 | 4026.75 | 0.042159
SPL-2 | Project Signboard (COA) |  | ea. | 1 | 7805.7 | 7805.7 | 0.081723 | 0 | 1 | 1 | 0 | 7805.7 | 7805.7 | 0.081723
SPL-3 | Const. Safety and Health |  | l.s. | 1 | 51542.4 | 51542.4 | 0.53963 | 1 | 0 | 1 | 51542.4 | 0 | 51542.4 | 0.53963
TOTAL AMOUNT | [5 empty] | 9551425.52 | 100 |  |  |  | 3267541.4022 | 495612.8697 | 3763154.2719 | 39.3989 | 5.1889
|  | Prepared By : |  |  |  |  | Checked By:
|  |  | __________________________ |  |  |  |  | _______________________________
|  |  | CHARLON O. QUIMINALES |  |  |  |  | MYRNA O. POLICARPIO
|  |  | Project Engineer |  |  |  |  | General Manager
F-PIM-004
Rev. 0 09/19/14
WEEKLY ACCOMPLISHMENT
REPORT

## Oct 7
CONCRETING OF TANAWIN ROAD - LAGUNITA ROAD
BRGY. TUNGKONG MANGGA, SAN JOSE DEL MONTE CITY, BULACAN
WORK ACCOMPLISHMENT: OCTOBER 7, 2016
Item No. | Work Description |  | Unit | Qty | Unit Cost | Amount | Weight (%) | Accomplishment (Quantity) |  |  | Amount |  |  | Weight accomplished (%)
[8 empty] | Previous | This period | To Date | Previous | This Period | To Date
100 | Clearing and Grubbing |  | sq.m. | 1758.8 | 16.01 | 28158.39 | 0.29481 | 847.6 | 307.2 | 1154.8 | 13570.077 | 4918.2723 | 18488.3493 | 0.19357
103 | Structure Excavation |  | cu.m. | 272.8 | 225.41 | 61491.85 | 0.6438 | 52.4 | 0 | 52.4 | 11811.4844 | 0 | 11811.4844 | 0.12366
105 | Subgrade Preparation |  | sq.m. | 6155.8 | 15.11 | 93014.14 | 0.97382 | 2966.6 | 1075.2 | 4041.8 | 44825.327 | 16246.2723 | 61071.5993 | 0.6394
200 | Aggregate Sub Base Coarse |  | cu.m. | 871 | 618.0757 | 538343.93 | 5.6363 | 419.7519 | 152.1328 | 571.8847 | 259438.4325 | 94029.5971 | 353468.0295 | 3.7007
201 | Aggregate Base Coarse |  | cu.m. | 581 | 731.2165 | 424836.81 | 4.4479 | 279.9952 | 101.4801 | 381.4753 | 204737.139 | 74203.9277 | 278941.0667 | 2.9204
311 | PCCP(250mmthk @ 14days conc.) |  | sq.m. | 5276.4 | 1124.5 | 5933311.8 | 62.1196 | 2542.8 | 921.6 | 3464.4 | 2859378.6 | 1036339.2 | 3895717.8 | 40.7868
404 | Reinforcing Steel Bar |  | kgs. | 5080.2 | 46.48 | 236127.7 | 2.4722 | 0 | 1524.06 | 1524.06 | 0 | 70838.31 | 70838.31 | 0.74165
405 | Structural Concrete Class "A" |  | cu.m. | 65.82 | 6001.8899 | 395044.39 | 4.136 | 0 | 19.746 | 19.746 | 0 | 118513.317 | 118513.317 | 1.2408
505 | Grouted Riprap |  | cu.m. | 682 | 2606.63 | 1777721.66 | 18.6121 | 117.4 | 88.24 | 205.64 | 306018.362 | 230009.0312 | 536027.3932 | 5.612
SPL-1 | Project Signboard (DPWH) |  | ea. | 1 | 4026.75 | 4026.75 | 0.042159 | 1 | 0 | 1 | 4026.75 | 0 | 4026.75 | 0.042159
SPL-2 | Project Signboard (COA) |  | ea. | 1 | 7805.7 | 7805.7 | 0.081723 | 1 | 0 | 1 | 7805.7 | 0 | 7805.7 | 0.081723
SPL-3 | Const. Safety and Health |  | l.s. | 1 | 51542.4 | 51542.4 | 0.53963 | 1 | 0 | 1 | 51542.4 | 0 | 51542.4 | 0.53963
TOTAL AMOUNT | [5 empty] | 9551425.52 | 100 |  |  |  | 3763154.2719 | 1645097.9276 | 5408252.1995 | 56.6225 | 22.4125
|  | Prepared By : |  |  |  |  | Checked By:
|  |  | __________________________ |  |  |  |  | _______________________________
|  |  | CHARLON O. QUIMINALES |  |  |  |  | MYRNA O. POLICARPIO
|  |  | Project Engineer |  |  |  |  | General Manager
F-PIM-004
Rev. 0 09/19/14
1812
WEEKLY ACCOMPLISHMENT
REPORT

## Oct 13
CONCRETING OF TANAWIN ROAD - LAGUNITA ROAD
BRGY. TUNGKONG MANGGA, SAN JOSE DEL MONTE CITY, BULACAN
WORK ACCOMPLISHMENT: OCTOBER 13, 2016
Item No. | Work Description |  | Unit | Qty | Unit Cost | Amount | Weight (%) | Accomplishment (Quantity) |  |  | Amount |  |  | Weight accomplished (%)
[8 empty] | Previous | This period | To Date | Previous | This Period | To Date
100 | Clearing and Grubbing |  | sq.m. | 1758.8 | 16.01 | 28158.39 | 0.29481 | 1154.8 | 132 | 1286.8 | 18488.3493 | 2113.3202 | 20601.6695 | 0.21569
103 | Structure Excavation |  | cu.m. | 272.8 | 225.41 | 61491.85 | 0.6438 | 52.4 | 5.6 | 58 | 11811.4844 | 1262.296 | 13073.7804 | 0.13688
105 | Subgrade Preparation |  | sq.m. | 6155.8 | 15.11 | 93014.14 | 0.97382 | 4041.8 | 462 | 4503.8 | 61071.5993 | 6980.8202 | 68052.4195 | 0.71248
200 | Aggregate Sub Base Coarse |  | cu.m. | 871 | 618.0757 | 538343.93 | 5.6363 | 571.8847 | 65.3696 | 637.2543 | 353468.0295 | 40403.3425 | 393871.372 | 4.1237
201 | Aggregate Base Coarse |  | cu.m. | 581 | 731.2165 | 424836.81 | 4.4479 | 381.4753 | 43.6047 | 425.0801 | 278941.0667 | 31884.5002 | 310825.5669 | 3.2542
311 | PCCP(250mmthk @ 14days conc.) |  | sq.m. | 5276.4 | 1124.5 | 5933311.8 | 62.1196 | 3464.4 | 0 | 3464.4 | 3895717.8 | 0 | 3895717.8 | 40.7868
404 | Reinforcing Steel Bar |  | kgs. | 5080.2 | 46.48 | 236127.7 | 2.4722 | 1524.06 | 1524.06 | 3048.12 | 70838.31 | 70838.31 | 141676.62 | 1.4833
405 | Structural Concrete Class "A" |  | cu.m. | 65.82 | 6001.8899 | 395044.39 | 4.136 | 19.746 | 19.746 | 39.492 | 118513.317 | 118513.317 | 237026.634 | 2.4816
505 | Grouted Riprap |  | cu.m. | 682 | 2606.63 | 1777721.66 | 18.6121 | 205.64 | 5.36 | 211 | 536027.3932 | 13971.5368 | 549998.93 | 5.7583
SPL-1 | Project Signboard (DPWH) |  | ea. | 1 | 4026.75 | 4026.75 | 0.042159 | 1 | 0 | 1 | 4026.75 | 0 | 4026.75 | 0.042159
SPL-2 | Project Signboard (COA) |  | ea. | 1 | 7805.7 | 7805.7 | 0.081723 | 1 | 0 | 1 | 7805.7 | 0 | 7805.7 | 0.081723
SPL-3 | Const. Safety and Health |  | l.s. | 1 | 51542.4 | 51542.4 | 0.53963 | 1 | 0 | 1 | 51542.4 | 0 | 51542.4 | 0.53963
TOTAL AMOUNT | [5 empty] | 9551425.52 | 100 |  |  |  | 5408252.1995 | 285967.4428 | 5694219.6423 | 59.6164 | 2.994
|  | Prepared By : |  |  |  |  | Checked By:
|  |  | __________________________ |  |  |  |  | _______________________________
|  |  | CHARLON O. QUIMINALES |  |  |  |  | MYRNA O. POLICARPIO
|  |  | Project Engineer |  |  |  |  | General Manager
F-PIM-004
Rev. 0 09/19/14
1812
WEEKLY ACCOMPLISHMENT
REPORT

## Oct 21
CONCRETING OF TANAWIN ROAD - LAGUNITA ROAD
BRGY. TUNGKONG MANGGA, SAN JOSE DEL MONTE CITY, BULACAN
WORK ACCOMPLISHMENT: OCTOBER 21, 2016
Item No. | Work Description |  | Unit | Qty | Unit Cost | Amount | Weight (%) | Accomplishment (Quantity) |  |  | Amount |  |  | Weight accomplished (%)
[8 empty] | Previous | This period | To Date | Previous | This Period | To Date
100 | Clearing and Grubbing |  | sq.m. | 1758.8 | 16.01 | 28158.39 | 0.29481 | 1286.8 | 50.36 | 1337.16 | 20601.6695 | 806.2637 | 21407.9331 | 0.22413
103 | Structure Excavation |  | cu.m. | 272.8 | 225.41 | 61491.85 | 0.6438 | 58 | 16 | 74 | 13073.7804 | 3606.5601 | 16680.3405 | 0.17464
105 | Subgrade Preparation |  | sq.m. | 6155.8 | 15.11 | 93014.14 | 0.97382 | 4503.8 | 176.26 | 4680.06 | 68052.4195 | 2663.2887 | 70715.7081 | 0.74037
200 | Aggregate Sub Base Coarse |  | cu.m. | 871 | 618.0757 | 538343.93 | 5.6363 | 637.2543 | 24.9395 | 662.1937 | 393871.372 | 15414.4873 | 409285.8594 | 4.2851
201 | Aggregate Base Coarse |  | cu.m. | 581 | 731.2165 | 424836.81 | 4.4479 | 425.0801 | 16.6359 | 441.7159 | 310825.5669 | 12164.4199 | 322989.9868 | 3.3816
311 | PCCP(250mmthk @ 14days conc.) |  | sq.m. | 5276.4 | 1124.5 | 5933311.8 | 62.1196 | 3464.4 | 151.08 | 3615.48 | 3895717.8 | 169889.46 | 4065607.26 | 42.5655
404 | Reinforcing Steel Bar |  | kgs. | 5080.2 | 46.48 | 236127.7 | 2.4722 | 3048.12 | 1016.04 | 4064.16 | 141676.62 | 47225.54 | 188902.16 | 1.9777
405 | Structural Concrete Class "A" |  | cu.m. | 65.82 | 6001.8899 | 395044.39 | 4.136 | 39.492 | 13.164 | 52.656 | 237026.634 | 79008.878 | 316035.512 | 3.3088
505 | Grouted Riprap |  | cu.m. | 682 | 2606.63 | 1777721.66 | 18.6121 | 211 | 48 | 259 | 549998.93 | 125118.24 | 675117.17 | 7.0682
SPL-1 | Project Signboard (DPWH) |  | ea. | 1 | 4026.75 | 4026.75 | 0.042159 | 1 | 0 | 1 | 4026.75 | 0 | 4026.75 | 0.042159
SPL-2 | Project Signboard (COA) |  | ea. | 1 | 7805.7 | 7805.7 | 0.081723 | 1 | 0 | 1 | 7805.7 | 0 | 7805.7 | 0.081723
SPL-3 | Const. Safety and Health |  | l.s. | 1 | 51542.4 | 51542.4 | 0.53963 | 1 | 0 | 1 | 51542.4 | 0 | 51542.4 | 0.53963
TOTAL AMOUNT | [5 empty] | 9551425.52 | 100 |  |  |  | 5694219.6423 | 455897.1377 | 6150116.78 | 64.3895 | 7.7671
|  | Prepared By : |  |  |  |  | Checked By:
|  |  | __________________________ |  |  |  |  | _______________________________
|  |  | CHARLON O. QUIMINALES |  |  |  |  | MYRNA O. POLICARPIO
|  |  | Project Engineer |  |  |  |  | General Manager
F-PIM-004
Rev. 0 09/19/14
1660.92
WEEKLY ACCOMPLISHMENT
REPORT

## Oct 27
CONCRETING OF TANAWIN ROAD - LAGUNITA ROAD
BRGY. TUNGKONG MANGGA, SAN JOSE DEL MONTE CITY, BULACAN
WORK ACCOMPLISHMENT: OCTOBER 27, 2016
Item No. | Work Description |  | Unit | Qty | Unit Cost | Amount | Weight (%) | Accomplishment (Quantity) |  |  | Amount |  |  | Weight accomplished (%)
[8 empty] | Previous | This period | To Date | Previous | This Period | To Date
100 | Clearing and Grubbing |  | sq.m. | 1758.8 | 16.01 | 28158.39 | 0.29481 | 1337.16 | 52.5 | 1389.66 | 21407.9331 | 840.5251 | 22248.4582 | 0.23293
103 | Structure Excavation |  | cu.m. | 272.8 | 225.41 | 61491.85 | 0.6438 | 74 | 10.4 | 84.4 | 16680.3405 | 2344.2641 | 19024.6046 | 0.19918
105 | Subgrade Preparation |  | sq.m. | 6155.8 | 15.11 | 93014.14 | 0.97382 | 4680.06 | 183.75 | 4863.81 | 70715.7081 | 2776.4626 | 73492.1707 | 0.76944
200 | Aggregate Sub Base Coarse |  | cu.m. | 871 | 618.0757 | 538343.93 | 5.6363 | 662.1937 | 25.9993 | 688.193 | 409285.8594 | 16069.5112 | 425355.3706 | 4.4533
201 | Aggregate Base Coarse |  | cu.m. | 581 | 731.2165 | 424836.81 | 4.4479 | 441.7159 | 17.3428 | 459.0587 | 322989.9868 | 12681.3353 | 335671.3221 | 3.5144
311 | PCCP(250mmthk @ 14days conc.) |  | sq.m. | 5276.4 | 1124.5 | 5933311.8 | 62.1196 | 3615.48 | 157.5 | 3772.98 | 4065607.26 | 177108.75 | 4242716.01 | 44.4197
404 | Reinforcing Steel Bar |  | kgs. | 5080.2 | 46.48 | 236127.7 | 2.4722 | 4064.16 | 508.02 | 4572.18 | 188902.16 | 23612.77 | 212514.93 | 2.225
405 | Structural Concrete Class "A" |  | cu.m. | 65.82 | 6001.8899 | 395044.39 | 4.136 | 52.656 | 6.582 | 59.238 | 316035.512 | 39504.439 | 355539.951 | 3.7224
505 | Grouted Riprap |  | cu.m. | 682 | 2606.63 | 1777721.66 | 18.6121 | 259 | 36.4 | 295.4 | 675117.17 | 94881.332 | 769998.502 | 8.0616
SPL-1 | Project Signboard (DPWH) |  | ea. | 1 | 4026.75 | 4026.75 | 0.042159 | 1 | 0 | 1 | 4026.75 | 0 | 4026.75 | 0.042159
SPL-2 | Project Signboard (COA) |  | ea. | 1 | 7805.7 | 7805.7 | 0.081723 | 1 | 0 | 1 | 7805.7 | 0 | 7805.7 | 0.081723
SPL-3 | Const. Safety and Health |  | l.s. | 1 | 51542.4 | 51542.4 | 0.53963 | 1 | 0 | 1 | 51542.4 | 0 | 51542.4 | 0.53963
TOTAL AMOUNT | [5 empty] | 9551425.52 | 100 |  |  |  | 6150116.78 | 369819.3892 | 6519936.1692 | 68.2614 | 11.6389
|  | Prepared By : |  |  |  |  | Checked By:
|  |  | __________________________ |  |  |  |  | _______________________________
|  |  | CHARLON O. QUIMINALES |  |  |  |  | MYRNA O. POLICARPIO
|  |  | Project Engineer |  |  |  |  | General Manager
F-PIM-004
Rev. 0 09/19/14
1503.42
WEEKLY ACCOMPLISHMENT
REPORT

## Nov 4
CONCRETING OF TANAWIN ROAD - LAGUNITA ROAD
BRGY. TUNGKONG MANGGA, SAN JOSE DEL MONTE CITY, BULACAN
WORK ACCOMPLISHMENT: NOVEMBER 4, 2016
Item No. | Work Description |  | Unit | Qty | Unit Cost | Amount | Weight (%) | Accomplishment (Quantity) |  |  | Amount |  |  | Weight accomplished (%)
[8 empty] | Previous | This period | To Date | Previous | This Period | To Date
100 | Clearing and Grubbing |  | sq.m. | 1758.8 | 16.01 | 28158.39 | 0.29481 | 1389.66 | 9.54 | 1399.2 | 22248.4582 | 152.7354 | 22401.1936 | 0.23453
103 | Structure Excavation |  | cu.m. | 272.8 | 225.41 | 61491.85 | 0.6438 | 84.4 | 24.4 | 108.8 | 19024.6046 | 5500.0042 | 24524.6088 | 0.25676
105 | Subgrade Preparation |  | sq.m. | 6155.8 | 15.11 | 93014.14 | 0.97382 | 4863.81 | 33.39 | 4897.2 | 73492.1707 | 504.5229 | 73996.6936 | 0.77472
200 | Aggregate Sub Base Coarse |  | cu.m. | 871 | 618.0757 | 538343.93 | 5.6363 | 688.193 | 4.7244 | 692.9174 | 425355.3706 | 2920.0598 | 428275.4303 | 4.4839
201 | Aggregate Base Coarse |  | cu.m. | 581 | 731.2165 | 424836.81 | 4.4479 | 459.0587 | 3.1514 | 462.2101 | 335671.3221 | 2304.3798 | 337975.7019 | 3.5385
311 | PCCP(250mmthk @ 14days conc.) |  | sq.m. | 5276.4 | 1124.5 | 5933311.8 | 62.1196 | 3772.98 | 64.62 | 3837.6 | 4242716.01 | 72665.19 | 4315381.2 | 45.1805 | 62.1196 | 45.1805
404 | Reinforcing Steel Bar |  | kgs. | 5080.2 | 46.48 | 236127.7 | 2.4722 | 4572.18 | 254.01 | 4826.19 | 212514.93 | 11806.385 | 224321.315 | 2.3486 | 100 | 72.7314
405 | Structural Concrete Class "A" |  | cu.m. | 65.82 | 6001.8899 | 395044.39 | 4.136 | 59.238 | 3.291 | 62.529 | 355539.951 | 19752.2195 | 375292.1705 | 3.9292
505 | Grouted Riprap |  | cu.m. | 682 | 2606.63 | 1777721.66 | 18.6121 | 295.4 | 85.4 | 380.8 | 769998.502 | 222606.202 | 992604.704 | 10.3922
SPL-1 | Project Signboard (DPWH) |  | ea. | 1 | 4026.75 | 4026.75 | 0.042159 | 1 | 0 | 1 | 4026.75 | 0 | 4026.75 | 0.042159
SPL-2 | Project Signboard (COA) |  | ea. | 1 | 7805.7 | 7805.7 | 0.081723 | 1 | 0 | 1 | 7805.7 | 0 | 7805.7 | 0.081723
SPL-3 | Const. Safety and Health |  | l.s. | 1 | 51542.4 | 51542.4 | 0.53963 | 1 | 0 | 1 | 51542.4 | 0 | 51542.4 | 0.53963
TOTAL AMOUNT | [5 empty] | 9551425.52 | 100 |  |  |  | 6519936.1692 | 338211.6985 | 6858147.8677 | 71.8023 | 15.1799
|  | Prepared By : |  |  |  |  | Checked By:
|  |  | __________________________ |  |  |  |  | _______________________________
|  |  | CHARLON O. QUIMINALES |  |  |  |  | MYRNA O. POLICARPIO
|  |  | Project Engineer |  |  |  |  | General Manager
F-PIM-004
Rev. 0 09/19/14
[16 empty] | monthly accomplishment | [5 empty] | target completion
[10 empty] | 1438.8 | [5 empty] | august | september | october |  |  | november | 2016-12-08
[16 empty] | 7.19 | 39.4 | 68.26 |  |  | 71.8
[16 empty] | 7.19 | 32.21 | 28.86 |  |  | 3.54
[15 empty] | 1758.8 | 0 | 847.6 | 1389.66 | 369.14 | 0.061875
[15 empty] | 272.8 | 0 | 52.4 | 84.4 | 188.4 | 0.44462
[15 empty] | 6155.8 | 945 | 2966.6 | 4863.81 | 1291.99 | 0.20439
[15 empty] | 871 | 77.8987 | 419.7519 | 688.193 | 182.807 | 1.1829
[15 empty] | 581 | 51.9623 | 279.9952 | 459.0587 | 121.9413 | 0.93353
[15 empty] | 5276.4 | 471.9 | 2542.8 | 3772.98 | 1503.42 | 17.6999
[15 empty] | 5080.2 | 0 | 0 | 4572.18 | 508.02 | 0.24722
[15 empty] | 65.82 | 0 | 0 | 59.238 | 6.582 | 0.4136
[15 empty] | 682 | 0 | 117.4 | 295.4 | 386.6 | 10.5505
[15 empty] | 1 | 1 | 1 | 1 | 0 | 0
[15 empty] | 1 | 0 | 1 | 1 | 0 | 0
[15 empty] | 1 | 1 | 1 | 1 | 0 | 0
31.7386
99.9986
monthly schedule
[16 empty] | ntp | 2016-08-08
[16 empty] | actual start | 2016-08-18
[16 empty] | expiry | 2016-09-24
[16 empty] | target | 2016-12-08
[16 empty] | august | september | october |  |  | november | december
WEEKLY ACCOMPLISHMENT
REPORT

## Nov 11
CONCRETING OF TANAWIN ROAD - LAGUNITA ROAD
BRGY. TUNGKONG MANGGA, SAN JOSE DEL MONTE CITY, BULACAN
WORK ACCOMPLISHMENT: NOVEMBER 11, 2016
Item No. | Work Description |  | Unit | Qty | Unit Cost | Amount | Weight (%) | Accomplishment (Quantity) |  |  | Amount |  |  | Weight accomplished (%)
[8 empty] | Previous | This period | To Date | Previous | This Period | To Date
100 | Clearing and Grubbing |  | sq.m. | 1758.8 | 16.01 | 28158.39 | 0.29481 | 1399.2 | 89 | 1488.2 | 22401.1936 | 1424.8901 | 23826.0837 | 0.24945
103 | Structure Excavation |  | cu.m. | 272.8 | 225.41 | 61491.85 | 0.6438 | 108.8 | 13.04 | 121.84 | 24524.6088 | 2939.3465 | 27463.9553 | 0.28754
105 | Subgrade Preparation |  | sq.m. | 6155.8 | 15.11 | 93014.14 | 0.97382 | 4897.2 | 311.5 | 5208.7 | 73996.6936 | 4706.7651 | 78703.4587 | 0.824
200 | Aggregate Sub Base Coarse |  | cu.m. | 871 | 618.0757 | 538343.93 | 5.6363 | 692.9174 | 44.0749 | 736.9924 | 428275.4303 | 27241.6476 | 455517.0779 | 4.7691
201 | Aggregate Base Coarse |  | cu.m. | 581 | 731.2165 | 424836.81 | 4.4479 | 462.2101 | 29.4002 | 491.6103 | 337975.7019 | 21497.8827 | 359473.5846 | 3.7636
311 | PCCP(250mmthk @ 14days conc.) |  | sq.m. | 5276.4 | 1124.5 | 5933311.8 | 62.1196 | 3837.6 | 627 | 4464.6 | 4315381.2 | 705061.5 | 5020442.7 | 52.5622 | 62.1196 | 52.5622
404 | Reinforcing Steel Bar |  | kgs. | 5080.2 | 46.48 | 236127.7 | 2.4722 | 4826.19 | 254.01 | 5080.2 | 224321.315 | 11806.385 | 236127.7 | 2.4722 | 100 | 84.6145
405 | Structural Concrete Class "A" |  | cu.m. | 65.82 | 6001.8899 | 395044.39 | 4.136 | 62.529 | 3.291 | 65.82 | 375292.1705 | 19752.2195 | 395044.39 | 4.136
505 | Grouted Riprap |  | cu.m. | 682 | 2606.63 | 1777721.66 | 18.6121 | 380.8 | 45.64 | 426.44 | 992604.704 | 118966.5932 | 1111571.2972 | 11.6378 | 255.56
SPL-1 | Project Signboard (DPWH) |  | ea. | 1 | 4026.75 | 4026.75 | 0.042159 | 1 | 0 | 1 | 4026.75 | 0 | 4026.75 | 0.042159 | 720.5
SPL-2 | Project Signboard (COA) |  | ea. | 1 | 7805.7 | 7805.7 | 0.081723 | 1 | 0 | 1 | 7805.7 | 0 | 7805.7 | 0.081723
SPL-3 | Const. Safety and Health |  | l.s. | 1 | 51542.4 | 51542.4 | 0.53963 | 1 | 0 | 1 | 51542.4 | 0 | 51542.4 | 0.53963
TOTAL AMOUNT | [5 empty] | 9551425.52 | 100 |  |  |  | 6858147.8677 | 913397.2297 | 7771545.0974 | 81.3653 | 24.7428
|  | Prepared By : |  |  |  |  | Checked By:
|  |  | __________________________ |  |  |  |  | _______________________________
|  |  | CHARLON O. QUIMINALES |  |  |  |  | MYRNA O. POLICARPIO
|  |  | Project Engineer |  |  |  |  | General Manager
F-PIM-004
Rev. 0 09/19/14
[16 empty] | monthly accomplishment | [5 empty] | target completion
[10 empty] | 811.8 | [5 empty] | august | september | october |  |  | november | 2016-12-08
[10 empty] | 255.56 | [5 empty] | 7.19 | 39.4 | 68.26 |  |  | 71.8
[10 empty] | 350 | [5 empty] | 7.19 | 32.21 | 28.86 |  |  | 3.54
[15 empty] | 1758.8 | 0 | 847.6 | 1389.66 | 369.14 | 0.061875
[15 empty] | 272.8 | 0 | 52.4 | 84.4 | 188.4 | 0.44462
[15 empty] | 6155.8 | 945 | 2966.6 | 4863.81 | 1291.99 | 0.20439
[15 empty] | 871 | 77.8987 | 419.7519 | 688.193 | 182.807 | 1.1829
[15 empty] | 581 | 51.9623 | 279.9952 | 459.0587 | 121.9413 | 0.93353
[15 empty] | 5276.4 | 471.9 | 2542.8 | 3772.98 | 1503.42 | 17.6999
[15 empty] | 5080.2 | 0 | 0 | 4572.18 | 508.02 | 0.24722
[15 empty] | 65.82 | 0 | 0 | 59.238 | 6.582 | 0.4136
[15 empty] | 682 | 0 | 117.4 | 295.4 | 386.6 | 10.5505
[15 empty] | 1 | 1 | 1 | 1 | 0 | 0
[15 empty] | 1 | 0 | 1 | 1 | 0 | 0
[15 empty] | 1 | 1 | 1 | 1 | 0 | 0
31.7386
99.9986
monthly schedule
[16 empty] | ntp | 2016-08-08
[16 empty] | actual start | 2016-08-18
[16 empty] | expiry | 2016-09-24
[16 empty] | target | 2016-12-08
[16 empty] | august | september | october |  |  | november | december
WEEKLY ACCOMPLISHMENT
REPORT

## Nov 18
CONCRETING OF TANAWIN ROAD - LAGUNITA ROAD
BRGY. TUNGKONG MANGGA, SAN JOSE DEL MONTE CITY, BULACAN
WORK ACCOMPLISHMENT: NOVEMBER 18, 2016
Item No. | Work Description |  | Unit | Qty | Unit Cost | Amount | Weight (%) | Accomplishment (Quantity) |  |  | Amount |  |  | Weight accomplished (%)
[8 empty] | Previous | This period | To Date | Previous | This Period | To Date
100 | Clearing and Grubbing |  | sq.m. | 1758.8 | 16.01 | 28158.39 | 0.29481 | 1488.2 | 64.5 | 1552.7 | 23826.0837 | 1032.6451 | 24858.7288 | 0.26026
103 | Structure Excavation |  | cu.m. | 272.8 | 225.41 | 61491.85 | 0.6438 | 121.84 | 16 | 137.84 | 27463.9553 | 3606.5601 | 31070.5154 | 0.3253
105 | Subgrade Preparation |  | sq.m. | 6155.8 | 15.11 | 93014.14 | 0.97382 | 5208.7 | 225.75 | 5434.45 | 78703.4587 | 3411.0826 | 82114.5413 | 0.85971
200 | Aggregate Sub Base Coarse |  | cu.m. | 871 | 618.0757 | 538343.93 | 5.6363 | 736.9924 | 31.9419 | 768.9343 | 455517.0779 | 19742.5423 | 475259.6203 | 4.9758
201 | Aggregate Base Coarse |  | cu.m. | 581 | 731.2165 | 424836.81 | 4.4479 | 491.6103 | 21.3069 | 512.9172 | 359473.5846 | 15579.9262 | 375053.5109 | 3.9267
311 | PCCP(250mmthk @ 14days conc.) |  | sq.m. | 5276.4 | 1124.5 | 5933311.8 | 62.1196 | 4464.6 | 193.5 | 4658.1 | 5020442.7 | 217590.75 | 5238033.45 | 54.8403 | 62.1196 | 54.8403
404 | Reinforcing Steel Bar |  | kgs. | 5080.2 | 46.48 | 236127.7 | 2.4722 | 5080.2 | 0 | 5080.2 | 236127.7 | 0 | 236127.7 | 2.4722 | 100 | 88.2818
405 | Structural Concrete Class "A" |  | cu.m. | 65.82 | 6001.8899 | 395044.39 | 4.136 | 65.82 | 0 | 65.82 | 395044.39 | 0 | 395044.39 | 4.136
505 | Grouted Riprap |  | cu.m. | 682 | 2606.63 | 1777721.66 | 18.6121 | 426.44 | 56 | 482.44 | 1111571.2972 | 145971.28 | 1257542.5772 | 13.166 | 199.56 | 656.7
SPL-1 | Project Signboard (DPWH) |  | ea. | 1 | 4026.75 | 4026.75 | 0.042159 | 1 | 0 | 1 | 4026.75 | 0 | 4026.75 | 0.042159
SPL-2 | Project Signboard (COA) |  | ea. | 1 | 7805.7 | 7805.7 | 0.081723 | 1 | 0 | 1 | 7805.7 | 0 | 7805.7 | 0.081723
SPL-3 | Const. Safety and Health |  | l.s. | 1 | 51542.4 | 51542.4 | 0.53963 | 1 | 0 | 1 | 51542.4 | 0 | 51542.4 | 0.53963
TOTAL AMOUNT | [5 empty] | 9551425.52 | 100 |  |  |  | 7771545.0974 | 406934.7863 | 8178479.8838 | 85.6258 | 29.0033
|  | Prepared By : |  |  |  |  | Checked By:
|  |  | __________________________ |  |  |  |  | _______________________________
|  |  | CHARLON O. QUIMINALES |  |  |  |  | MYRNA O. POLICARPIO
|  |  | Project Engineer |  |  |  |  | General Manager
F-PIM-004
Rev. 0 09/19/14
[16 empty] | monthly accomplishment | [5 empty] | target completion
[10 empty] | 618.3 | [5 empty] | august | september | october |  |  | november | 2016-12-08
[10 empty] | 199.56 | [5 empty] | 7.19 | 39.4 | 68.26 |  |  | 71.8
[10 empty] | 350 | [5 empty] | 7.19 | 32.21 | 28.86 |  |  | 3.54
[15 empty] | 1758.8 | 0 | 847.6 | 1389.66 | 369.14 | 0.061875
[15 empty] | 272.8 | 0 | 52.4 | 84.4 | 188.4 | 0.44462
[15 empty] | 6155.8 | 945 | 2966.6 | 4863.81 | 1291.99 | 0.20439
[15 empty] | 871 | 77.8987 | 419.7519 | 688.193 | 182.807 | 1.1829
[15 empty] | 581 | 51.9623 | 279.9952 | 459.0587 | 121.9413 | 0.93353
[15 empty] | 5276.4 | 471.9 | 2542.8 | 3772.98 | 1503.42 | 17.6999
[15 empty] | 5080.2 | 0 | 0 | 4572.18 | 508.02 | 0.24722
[15 empty] | 65.82 | 0 | 0 | 59.238 | 6.582 | 0.4136
[15 empty] | 682 | 0 | 117.4 | 295.4 | 386.6 | 10.5505
[15 empty] | 1 | 1 | 1 | 1 | 0 | 0
[15 empty] | 1 | 0 | 1 | 1 | 0 | 0
[15 empty] | 1 | 1 | 1 | 1 | 0 | 0
31.7386
99.9986
monthly schedule
[16 empty] | ntp | 2016-08-08
[16 empty] | actual start | 2016-08-18
[16 empty] | expiry | 2016-09-24
[16 empty] | target | 2016-12-08
[16 empty] | august | september | october |  |  | november | december
WEEKLY ACCOMPLISHMENT
REPORT

## Nov 24
CONCRETING OF TANAWIN ROAD - LAGUNITA ROAD
BRGY. TUNGKONG MANGGA, SAN JOSE DEL MONTE CITY, BULACAN
WORK ACCOMPLISHMENT: NOVEMBER 24, 2016
Item No. | Work Description |  | Unit | Qty | Unit Cost | Amount | Weight (%) | Accomplishment (Quantity) |  |  | Amount |  |  | Weight accomplished (%)
[8 empty] | Previous | This period | To Date | Previous | This Period | To Date
100 | Clearing and Grubbing |  | sq.m. | 1758.8 | 16.01 | 28158.39 | 0.29481 | 1552.7 | 125 | 1677.7 | 24858.7288 | 2001.2501 | 26859.9789 | 0.28121
103 | Structure Excavation |  | cu.m. | 272.8 | 225.41 | 61491.85 | 0.6438 | 137.84 | 0 | 137.84 | 31070.5154 | 0 | 31070.5154 | 0.3253
105 | Subgrade Preparation |  | sq.m. | 6155.8 | 15.11 | 93014.14 | 0.97382 | 5434.45 | 437.5 | 5871.95 | 82114.5413 | 6610.6251 | 88725.1664 | 0.92892
200 | Aggregate Sub Base Coarse |  | cu.m. | 871 | 618.0757 | 538343.93 | 5.6363 | 768.9343 | 61.903 | 830.8373 | 475259.6203 | 38260.741 | 513520.3612 | 5.3764
201 | Aggregate Base Coarse |  | cu.m. | 581 | 731.2165 | 424836.81 | 4.4479 | 512.9172 | 41.2924 | 554.2095 | 375053.5109 | 30193.6555 | 405247.1663 | 4.2428
311 | PCCP(250mmthk @ 14days conc.) |  | sq.m. | 5276.4 | 1124.5 | 5933311.8 | 62.1196 | 4658.1 | 375 | 5033.1 | 5238033.45 | 421687.5 | 5659720.95 | 59.2552 | 62.1196 | 59.2552
404 | Reinforcing Steel Bar |  | kgs. | 5080.2 | 46.48 | 236127.7 | 2.4722 | 5080.2 | 0 | 5080.2 | 236127.7 | 0 | 236127.7 | 2.4722 | 100 | 95.3889
405 | Structural Concrete Class "A" |  | cu.m. | 65.82 | 6001.8899 | 395044.39 | 4.136 | 65.82 | 0 | 65.82 | 395044.39 | 0 | 395044.39 | 4.136
505 | Grouted Riprap |  | cu.m. | 682 | 2606.63 | 1777721.66 | 18.6121 | 482.44 | 80 | 562.44 | 1257542.5772 | 208530.4 | 1466072.9772 | 15.3493 | 119.56
SPL-1 | Project Signboard (DPWH) |  | ea. | 1 | 4026.75 | 4026.75 | 0.042159 | 1 | 0 | 1 | 4026.75 | 0 | 4026.75 | 0.042159 | 576.5
SPL-2 | Project Signboard (COA) |  | ea. | 1 | 7805.7 | 7805.7 | 0.081723 | 1 | 0 | 1 | 7805.7 | 0 | 7805.7 | 0.081723
SPL-3 | Const. Safety and Health |  | l.s. | 1 | 51542.4 | 51542.4 | 0.53963 | 1 | 0 | 1 | 51542.4 | 0 | 51542.4 | 0.53963
TOTAL AMOUNT | [5 empty] | 9551425.52 | 100 |  |  |  | 8178479.8838 | 707284.1717 | 8885764.0555 | 93.0308 | 36.4083
|  | Prepared By : |  |  |  |  | Checked By:
|  |  | __________________________ |  |  |  |  | _______________________________
|  |  | CHARLON O. QUIMINALES |  |  |  |  | MYRNA O. POLICARPIO
|  |  | Project Engineer |  |  |  |  | General Manager
F-PIM-004
Rev. 0 09/19/14
[16 empty] | monthly accomplishment | [5 empty] | target completion
[10 empty] | 243.3 | [5 empty] | august | september | october |  |  | november | 2016-12-08
[10 empty] | 119.56 | [5 empty] | 7.19 | 39.4 | 68.26 |  |  | 71.8
[10 empty] | 350 | [5 empty] | 7.19 | 32.21 | 28.86 |  |  | 3.54
[15 empty] | 1758.8 | 0 | 847.6 | 1389.66 | 369.14 | 0.061875
[15 empty] | 272.8 | 0 | 52.4 | 84.4 | 188.4 | 0.44462
[15 empty] | 6155.8 | 945 | 2966.6 | 4863.81 | 1291.99 | 0.20439
[15 empty] | 871 | 77.8987 | 419.7519 | 688.193 | 182.807 | 1.1829
[15 empty] | 581 | 51.9623 | 279.9952 | 459.0587 | 121.9413 | 0.93353
[15 empty] | 5276.4 | 471.9 | 2542.8 | 3772.98 | 1503.42 | 17.6999
[15 empty] | 5080.2 | 0 | 0 | 4572.18 | 508.02 | 0.24722
[15 empty] | 65.82 | 0 | 0 | 59.238 | 6.582 | 0.4136
[15 empty] | 682 | 0 | 117.4 | 295.4 | 386.6 | 10.5505
[15 empty] | 1 | 1 | 1 | 1 | 0 | 0
[15 empty] | 1 | 0 | 1 | 1 | 0 | 0
[15 empty] | 1 | 1 | 1 | 1 | 0 | 0
31.7386
99.9986
monthly schedule
[16 empty] | ntp | 2016-08-08
[16 empty] | actual start | 2016-08-18
[16 empty] | expiry | 2016-09-24
[16 empty] | target | 2016-12-08
[16 empty] | august | september | october |  |  | november | december
WEEKLY ACCOMPLISHMENT
REPORT

## Dec 1
CONCRETING OF TANAWIN ROAD - LAGUNITA ROAD
BRGY. TUNGKONG MANGGA, SAN JOSE DEL MONTE CITY, BULACAN
WORK ACCOMPLISHMENT: DECEMBER 1, 2016
Item No. | Work Description |  | Unit | Qty | Unit Cost | Amount | Weight (%) | Accomplishment (Quantity) |  |  | Amount |  |  | Weight accomplished (%)
[8 empty] | Previous | This period | To Date | Previous | This Period | To Date
100 | Clearing and Grubbing |  | sq.m. | 1758.8 | 16.01 | 28158.39 | 0.29481 | 1677.7 | 81.1 | 1758.8 | 26859.9789 | 1298.4111 | 28158.39 | 0.29481
103 | Structure Excavation |  | cu.m. | 272.8 | 225.41 | 61491.85 | 0.6438 | 137.84 | 14 | 151.84 | 31070.5154 | 3155.7401 | 34226.2555 | 0.35834
105 | Subgrade Preparation |  | sq.m. | 6155.8 | 15.11 | 93014.14 | 0.97382 | 5871.95 | 283.85 | 6155.8 | 88725.1664 | 4288.9736 | 93014.14 | 0.97382 |  |  | 358
200 | Aggregate Sub Base Coarse |  | cu.m. | 871 | 618.0757 | 538343.93 | 5.6363 | 830.8373 | 40.1627 | 871 | 513520.3612 | 24823.5688 | 538343.93 | 5.6363
201 | Aggregate Base Coarse |  | cu.m. | 581 | 731.2165 | 424836.81 | 4.4479 | 554.2095 | 26.7905 | 581 | 405247.1663 | 19589.6437 | 424836.81 | 4.4479
311 | PCCP(250mmthk @ 14days conc.) |  | sq.m. | 5276.4 | 1124.5 | 5933311.8 | 62.1196 | 5033.1 | 243.3 | 5276.4 | 5659720.95 | 273590.85 | 5933311.8 | 62.1196 | 62.1196 | 62.1196
404 | Reinforcing Steel Bar |  | kgs. | 5080.2 | 46.48 | 236127.7 | 2.4722 | 5080.2 | 0 | 5080.2 | 236127.7 | 0 | 236127.7 | 2.4722 | 100 | 100
405 | Structural Concrete Class "A" |  | cu.m. | 65.82 | 6001.8899 | 395044.39 | 4.136 | 65.82 | 0 | 65.82 | 395044.39 | 0 | 395044.39 | 4.136
505 | Grouted Riprap |  | cu.m. | 682 | 2606.63 | 1777721.66 | 18.6121 | 562.44 | 79.4 | 641.84 | 1466072.9772 | 206966.422 | 1673039.3992 | 17.5161 | 40.16
SPL-1 | Project Signboard (DPWH) |  | ea. | 1 | 4026.75 | 4026.75 | 0.042159 | 1 | 0 | 1 | 4026.75 | 0 | 4026.75 | 0.042159
SPL-2 | Project Signboard (COA) |  | ea. | 1 | 7805.7 | 7805.7 | 0.081723 | 1 | 0 | 1 | 7805.7 | 0 | 7805.7 | 0.081723
SPL-3 | Const. Safety and Health |  | l.s. | 1 | 51542.4 | 51542.4 | 0.53963 | 1 | 0 | 1 | 51542.4 | 0 | 51542.4 | 0.53963
TOTAL AMOUNT | [5 empty] | 9551425.52 | 100 |  |  |  | 8885764.0555 | 533713.6092 | 9419477.6647 | 98.6186 | 41.9961
|  | Prepared By : |  |  |  |  | Checked By:
|  |  | __________________________ |  |  |  |  | _______________________________
|  |  | CHARLON O. QUIMINALES |  |  |  |  | MYRNA O. POLICARPIO
|  |  | Project Engineer |  |  |  |  | General Manager
F-PIM-004
Rev. 0 09/19/14
[16 empty] | monthly accomplishment | [5 empty] | target completion
[10 empty] | 0 | [5 empty] | august | september | october |  |  | november | 2016-12-08
[10 empty] | 40.16 | [5 empty] | 7.19 | 39.4 | 68.26 |  |  | 71.8
[10 empty] | 350 | [5 empty] | 7.19 | 32.21 | 28.86 |  |  | 3.54
[15 empty] | 1758.8 | 0 | 847.6 | 1389.66 | 369.14 | 0.061875
[15 empty] | 272.8 | 0 | 52.4 | 84.4 | 188.4 | 0.44462
[15 empty] | 6155.8 | 945 | 2966.6 | 4863.81 | 1291.99 | 0.20439
[15 empty] | 871 | 77.8987 | 419.7519 | 688.193 | 182.807 | 1.1829
[15 empty] | 581 | 51.9623 | 279.9952 | 459.0587 | 121.9413 | 0.93353
[15 empty] | 5276.4 | 471.9 | 2542.8 | 3772.98 | 1503.42 | 17.6999
[15 empty] | 5080.2 | 0 | 0 | 4572.18 | 508.02 | 0.24722
[15 empty] | 65.82 | 0 | 0 | 59.238 | 6.582 | 0.4136
[15 empty] | 682 | 0 | 117.4 | 295.4 | 386.6 | 10.5505
[15 empty] | 1 | 1 | 1 | 1 | 0 | 0
[15 empty] | 1 | 0 | 1 | 1 | 0 | 0
[15 empty] | 1 | 1 | 1 | 1 | 0 | 0
31.7386
99.9986
monthly schedule
[16 empty] | ntp | 2016-08-08
[16 empty] | actual start | 2016-08-18
[16 empty] | expiry | 2016-09-24
[16 empty] | target | 2016-12-08
[16 empty] | august | september | october |  |  | november | december
WEEKLY ACCOMPLISHMENT
REPORT

## Dec 8
CONCRETING OF TANAWIN ROAD - LAGUNITA ROAD
BRGY. TUNGKONG MANGGA, SAN JOSE DEL MONTE CITY, BULACAN
WORK ACCOMPLISHMENT: DECEMBER 8, 2016
Item No. | Work Description |  | Unit | Qty | Unit Cost | Amount | Weight (%) | Accomplishment (Quantity) |  |  | Amount |  |  | Weight accomplished (%)
[8 empty] | Previous | This period | To Date | Previous | This Period | To Date
100 | Clearing and Grubbing |  | sq.m. | 1758.8 | 16.01 | 28158.39 | 0.29481 | 1758.8 | 0 | 1758.8 | 28158.39 | 0 | 28158.39 | 0.29481
103 | Structure Excavation |  | cu.m. | 272.8 | 225.41 | 61491.85 | 0.6438 | 151.84 | 120.96 | 272.8 | 34226.2555 | 27265.5945 | 61491.85 | 0.6438
105 | Subgrade Preparation |  | sq.m. | 6155.8 | 15.11 | 93014.14 | 0.97382 | 6155.8 | 0 | 6155.8 | 93014.14 | 0 | 93014.14 | 0.97382
200 | Aggregate Sub Base Coarse |  | cu.m. | 871 | 618.0757 | 538343.93 | 5.6363 | 871 | 0 | 871 | 538343.93 | 0 | 538343.93 | 5.6363
201 | Aggregate Base Coarse |  | cu.m. | 581 | 731.2165 | 424836.81 | 4.4479 | 581 | 0 | 581 | 424836.81 | 0 | 424836.81 | 4.4479
311 | PCCP(250mmthk @ 14days conc.) |  | sq.m. | 5276.4 | 1124.5 | 5933311.8 | 62.1196 | 5276.4 | 0 | 5276.4 | 5933311.8 | 0 | 5933311.8 | 62.1196 | 62.1196 | 62.1196
404 | Reinforcing Steel Bar |  | kgs. | 5080.2 | 46.48 | 236127.7 | 2.4722 | 5080.2 | 0 | 5080.2 | 236127.7 | 0 | 236127.7 | 2.4722 | 100 | 100
405 | Structural Concrete Class "A" |  | cu.m. | 65.82 | 6001.8899 | 395044.39 | 4.136 | 65.82 | 0 | 65.82 | 395044.39 | 0 | 395044.39 | 4.136
505 | Grouted Riprap |  | cu.m. | 682 | 2606.63 | 1777721.66 | 18.6121 | 641.84 | 40.16 | 682 | 1673039.3992 | 104682.2608 | 1777721.66 | 18.6121
SPL-1 | Project Signboard (DPWH) |  | ea. | 1 | 4026.75 | 4026.75 | 0.042159 | 1 | 0 | 1 | 4026.75 | 0 | 4026.75 | 0.042159
SPL-2 | Project Signboard (COA) |  | ea. | 1 | 7805.7 | 7805.7 | 0.081723 | 1 | 0 | 1 | 7805.7 | 0 | 7805.7 | 0.081723
SPL-3 | Const. Safety and Health |  | l.s. | 1 | 51542.4 | 51542.4 | 0.53963 | 1 | 0 | 1 | 51542.4 | 0 | 51542.4 | 0.53963
TOTAL AMOUNT | [5 empty] | 9551425.52 | 100 |  |  |  | 9419477.6647 | 131947.8553 | 9551425.52 | 100 | 43.3775
|  | Prepared By : |  |  |  |  | Checked By:
|  |  | __________________________ |  |  |  |  | _______________________________
|  |  | CHARLON O. QUIMINALES |  |  |  |  | MYRNA O. POLICARPIO
|  |  | Project Engineer |  |  |  |  | General Manager
F-PIM-004
Rev. 0 09/19/14
[16 empty] | monthly accomplishment | [5 empty] | target completion
[10 empty] | 0 | [5 empty] | august | september | october |  |  | november | 2016-12-08
[10 empty] | 0 | [5 empty] | 7.19 | 39.4 | 68.26 |  |  | 71.8
[10 empty] | 350 | [5 empty] | 7.19 | 32.21 | 28.86 |  |  | 3.54
[15 empty] | 1758.8 | 0 | 847.6 | 1389.66 | 369.14 | 0.061875
[15 empty] | 272.8 | 0 | 52.4 | 84.4 | 188.4 | 0.44462
[15 empty] | 6155.8 | 945 | 2966.6 | 4863.81 | 1291.99 | 0.20439
[15 empty] | 871 | 77.8987 | 419.7519 | 688.193 | 182.807 | 1.1829
[15 empty] | 581 | 51.9623 | 279.9952 | 459.0587 | 121.9413 | 0.93353
[15 empty] | 5276.4 | 471.9 | 2542.8 | 3772.98 | 1503.42 | 17.6999
[15 empty] | 5080.2 | 0 | 0 | 4572.18 | 508.02 | 0.24722
[15 empty] | 65.82 | 0 | 0 | 59.238 | 6.582 | 0.4136
[15 empty] | 682 | 0 | 117.4 | 295.4 | 386.6 | 10.5505
[15 empty] | 1 | 1 | 1 | 1 | 0 | 0
[15 empty] | 1 | 0 | 1 | 1 | 0 | 0
[15 empty] | 1 | 1 | 1 | 1 | 0 | 0
31.7386
99.9986
monthly schedule
[16 empty] | ntp | 2016-08-08
[16 empty] | actual start | 2016-08-18
[16 empty] | expiry | 2016-09-24
[16 empty] | target | 2016-12-08
[16 empty] | august | september | october |  |  | november | december
WEEKLY ACCOMPLISHMENT
REPORT